## Project Timeline
Phase | 2023-03-12 | 2023-03-19 | 2023-03-26 | 2023-04-02 | 2023-04-09 | 2023-04-16 | Deadline 1 | Project Proposal Document Due
Exploratory Data Analysis | [6 empty] | Deadline 2 | Plan Presentation Video Due
Data Wrangling and Cleaning | [6 empty] | Deadline 3 | Progress Report Due
Modeling | [6 empty] | Deadline 4 | Final Report and Code Due
Feature Engineering and Tweaking the Model
Reporting